## Product Backlog
PRODUCT BACKLOG ¦ Bacteria AI Detection & Quantification ¦ EP7 Group
Module: COS6032-E ¦ Team: Kiran · Bandika · Jenish ¦ Supervisor: Dr Kulvinder Panesar ¦ Client: Dr Maria Katsikogianni
ID | User Story | Acceptance Criteria | Priority | Story Points | Assigned To | Sprint
PB-01 | As a team, we want a structured GitHub repository so that all project files are organised and version controlled. | Repo created with folders: data, preprocessing, model, results, documentation | Must Have | 5 | Kiran | Sprint 0
PB-02 | As a team, we want clearly assigned roles so that responsibilities are clear and work is not duplicated. | Roles documented in PID: Kiran (PM/Model), Bandika (Data), Jenish (Evaluation) | Must Have | 3 | All Members | Sprint 0
PB-03 | As a team, we want to meet the client to confirm objectives and success criteria. | Client goals documented and agreed; Dice ≥ 0.80 confirmed as success criterion | Must Have | 8 | All Members | Sprint 1
PB-04 | As a researcher, I want access to the fluorescent microscopy dataset so that I can begin analysis. | DeepBacs dataset received and stored on shared Google Drive in /raw/ folder | Must Have | 8 | Bandika | Sprint 1
PB-05 | As a developer, I want to visually inspect the images to understand noise, brightness, and fluorescence patterns. | Initial visual analysis completed; brightness range and noise patterns documented | Must Have | 5 | Bandika | Sprint 1
PB-06 | As a student, I want to review research papers on U-Net and bacterial imaging to justify our approach. | Literature review completed; ≥5 papers reviewed; U-Net justified as architecture | Must Have | 13 | Jenish | Sprint 2
PB-07 | As a developer, I want to understand encoder-decoder and skip connections in U-Net before implementation. | Architecture diagram produced; encoder, bottleneck, decoder components understood | Must Have | 8 | Jenish | Sprint 2
PB-08 | As a researcher, I want to study Dice Score, IoU, Precision, and Recall to properly evaluate the model. | Metrics defined and formulas documented; acceptable thresholds agreed with supervisor | Must Have | 8 | Bandika | Sprint 2
PB-09 | As a developer, I want to remove poor-quality or corrupted images to improve model performance. | 5-point cleaning pipeline run; zero corrupt/missing/empty files confirmed | Must Have | 8 | Bandika | Sprint 3
PB-10 | As a developer, I want to normalise, resize, and augment images so they are suitable for training. | All images resized to 256×256; normalised to [0,1]; masks binarised to {0,1} | Must Have | 13 | Bandika | Sprint 3
PB-11 | As a developer, I want to apply horizontal and vertical flipping to expand the training dataset artificially. | 28 original samples augmented to 84; 80/20 train/val split confirmed: 67/17 | Must Have | 5 | Kiran | Sprint 3
PB-12 | As a developer, I want to design the U-Net architecture tailored to the dataset. | Architecture designed: 4 encoder blocks, bottleneck, 4 decoder blocks, skip connections | Must Have | 13 | Kiran | Sprint 3
PB-13 | As a developer, I want to code the U-Net model using TensorFlow/Keras. | Model implemented; total parameters 1,940,817; model.summary() reviewed | Must Have | 21 | Kiran | Sprint 3
PB-14 | As a developer, I want to configure Dice+BCE combined loss and Adam optimiser. | Loss function compiled; lr=1e-4; metrics: dice_coefficient, accuracy | Must Have | 5 | Kiran | Sprint 3
PB-15 | As a developer, I want to train the U-Net model on the dataset to learn bacterial features. | Model trained for 150 epochs (early stopped at 110); best val Dice = 0.8235 at epoch 90 | Must Have | 21 | Kiran | Sprint 4
PB-16 | As a developer, I want to configure ModelCheckpoint, EarlyStopping, and ReduceLROnPlateau callbacks. | All callbacks active; best_model.h5 saved to Drive; LR reduced at epochs 79, 93, 103 | Must Have | 8 | Kiran | Sprint 4
PB-17 | As a researcher, I want to calculate Dice, IoU, Precision, and Recall on test data. | Dice=79.6%, IoU=66.2%, Precision=76.9%, Recall=83.3% computed on 5 test images | Must Have | 13 | Jenish | Sprint 4
PB-18 | As a researcher, I want training and validation curves plotted to confirm healthy learning. | Dice and Loss curves saved as PNG; no significant overfitting observed | Must Have | 5 | Jenish | Sprint 4
PB-19 | As a client, I want a numerical bacterial count from each image. | Basic connected-components counting implemented; count displayed per image | Must Have | 8 | Jenish | Sprint 4
PB-20 | As a client, I want improved counting that separates touching bacteria. | Watershed algorithm implemented; total error reduced from 64 to 14 (78% improvement) | Must Have | 13 | Jenish | Sprint 4
PB-21 | As a team, we want an end-to-end pipeline from image input to segmentation output. | Full inference pipeline working: upload → preprocess → predict → count → display | Must Have | 13 | Kiran | Sprint 4
PB-22 | As a client, I want an interactive dashboard to upload images and view results. | Streamlit app (app.py, 525 lines) deployed; image upload, mask display, metrics shown | Must Have | 13 | Kiran | Sprint 5
PB-23 | As a client, I want to export results as JSON, CSV, and PNG report. | All four export buttons working: JSON, CSV, Report PNG, Mask PNG | Should Have | 5 | Kiran | Sprint 5
PB-24 | As a client, I want the dashboard accessible via a public URL for the exhibition. | Live URL generated via localtunnel; accessible on any device on exhibition day | Must Have | 3 | Kiran | Sprint 5
PB-25 | As a team, we want a professional exhibition poster designed and printed. | A1 poster designed covering CDIO phases, results, team info; printed before 17 April | Must Have | 5 | All Members | Sprint 5
PB-26 | As a student, I need to submit the individual Element 2 completion report. | 3000-word report submitted to Canvas by 27 April 2026; FAIR report included | Must Have | 8 | All Members | Sprint 5
TOTAL STORY POINTS |  |  |  | 238

## RACI CHART
RACI CHART
Task | Task | Task | Task | Task
Phase 1- Initiation
Project Selection | R | A | C | I
Team Contract | R | A | C | I
Client Meeting | R | C | C | A
Phase 2 – Planning
Dataset Collection | C | R | A | I
Data Understanding | C | R | A | I
Phase 3 – Research & Design
Literature Review | C | A | R | I
Data Preprocessing | C | R | A | I
Pipeline Design | R | A | A | I
Phase 4 – Implementation
Model Development (U-Net) | C | R | A | I
Model Training | C | R | A | I
Phase 5 – Testing
Model Evaluation | C | A | R | I
Watershed Counting | C | R | A | I
Error Analysis | C | A | R | I
Phase 6 – Deployment
Dashboard Development | C | A | R | I
Final Testing | C | A | R | I
Demo Preparation | R | A | A | I
Final Submission | R | A | A | I

## Sprint Backlog
Sprint Backlog
Epic | User Story Title | Story | Story Points | Sprint
Project Setup | Create project repository | As a team, we want a structured GitHub repository so that all project files are organised and version controlled. | 5 | Sprint 0
Project Setup | Define team roles | As a team, we want clearly assigned roles so that responsibilities are clear and work is not duplicated. | 3 | Sprint 0
Data Management | Receive dataset | As a developer, I want to receive the fluorescent microscopic dataset so that I can begin analysis and modelling. | 8 | Sprint 1
Data Management | Organise dataset | As a developer, I want the dataset stored in structured folders (raw, processed, labels) so that it is easy to use. | 5 | Sprint 1
Understanding Data | Initial data inspection | As a researcher, I want to visually inspect the images to understand noise, brightness, and fluorescence patterns. | 5 | Sprint 1
Client Alignment | Define project goals | As a team, we want to meet the client to confirm objectives and success criteria. | 8 | Sprint 1
Research | Literature review | As a student, I want to review research papers on U-Net and bacterial imaging to justify our approach. | 13 | Sprint 2
Research | Study U-Net architecture | As a developer, I want to understand encoder-decoder and skip connections in U-Net before implementation. | 8 | Sprint 2
Research | Investigate evaluation metrics | As a researcher, I want to study Dice Score and IoU so that I can properly evaluate the model. | 8 | Sprint 2
Data Processing | Clean dataset | As a developer, I want to remove poor-quality or corrupted images to improve model performance. | 8 | Sprint 3
Data Processing | Image preprocessing | As a developer, I want to normalize and denoise images so that they are suitable for training. | 13 | Sprint 3
Model Development | Design U-Net model | As a developer, I want to design the U-Net architecture tailored to our dataset. | 13 | Sprint 3
Model Development | Implement U-Net in Python | As a developer, I want to code the U-Net model using TensorFlow or PyTorch. | 21 | Sprint 3
Model Development | Split dataset | As a developer, I want to split data into train/validation/test sets to avoid bias. | 5 | Sprint 3
Testing | Train U-Net model | As a developer, I want to train the U-Net model on the dataset to learn bacterial features. | 21 | Sprint 4
Testing | Tune hyperparameters | As a developer, I want to adjust learning rate, batch size, and epochs to improve performance. | 13 | Sprint 4
Evaluation | Evaluate model performance | As a researcher, I want to calculate Dice Score and IoU to measure segmentation quality. | 13 | Sprint 4
Results | Generate segmentation outputs | As a user, I want to see segmented images showing detected bacteria. | 8 | Sprint 4
Results | Bacterial quantification | As a client, I want a numerical bacterial count from each image. | 13 | Sprint 4
Deployment | Build prototype pipeline | As a team, we want an end-to-end system from image input to output. | 13 | Sprint 4

## Sprint Plan
SPRINT PLAN ¦ Bacteria AI Detection & Quantification ¦ EP7 Group ¦ COS6032-E
Sprint 0 — Project Initiation & Setup ¦ Sep – 12 Oct 2025
Sprint Goal: Establish team structure, tools, and communication channels before formal project start.
Backlog ID | Task | Owner | Points | Status | Sprint Total Story Points
PB-01 | Create GitHub repository | Kiran | 3 | Done | 6
PB-02 | Define and document team roles | All Members | 3 | Done
Sprint Outcome: GitHub repository created with structured folders; team roles defined and documented in PID.
Sprint 1 — Client Alignment & Data Acquisition ¦ 13 Oct – 9 Nov 2025
Sprint Goal: Meet client, confirm objectives, obtain the DeepBacs dataset, and perform initial exploration.
Backlog ID | Task | Owner | Points | Status | Sprint Total Story Points
PB-03 | Client kick-off meeting — confirm scope and success criteria | All Members | 8 | Done | 21
PB-04 | Receive DeepBacs fluorescence microscopy dataset | Bandika | 8 | Done
PB-05 | Initial data inspection and visual analysis | Bandika | 5 | Done
Sprint Outcome: Client meeting completed; dataset obtained; 28 train + 5 test image-mask pairs confirmed.
Sprint 2 — Background Research & Architecture Selection ¦ 10 Nov – 7 Dec 2025
Sprint Goal: Complete literature review, justify U-Net selection, and define evaluation metrics.
Backlog ID | Task | Owner | Points | Status | Sprint Total Story Points
PB-06 | Literature review: U-Net, bacterial imaging, segmentation | Jenish | 13 | Done | 29
PB-07 | Study U-Net encoder-decoder and skip connections | Jenish | 8 | Done
PB-08 | Define and document evaluation metrics (Dice, IoU, Precision, Recall) | Bandika | 8 | Done
Sprint Outcome: Literature review completed; U-Net selected and justified; Dice ≥ 0.80 agreed as success criterion.
Sprint 3 — Data Engineering & Model Development ¦ 8 Dec 2025 – 9 Jan 2026
Sprint Goal: Clean, preprocess, and augment the dataset; design and implement the U-Net model architecture.
Backlog ID | Task | Owner | Points | Status | Sprint Total Story Points
PB-09 | 5-point data cleaning pipeline | Bandika | 8 | Done | 65
PB-10 | Image normalisation, resize to 256×256, mask binarisation | Bandika | 13 | Done
PB-11 | Data augmentation: horizontal + vertical flip (28 → 84 samples) | Kiran | 5 | Done
PB-12 | U-Net architecture design: encoder, bottleneck, decoder, skip connections | Kiran | 13 | Done
PB-13 | U-Net implementation in TensorFlow/Keras (1,940,817 parameters) | Kiran | 21 | Done
PB-14 | Configure Dice+BCE loss function and Adam optimiser | Kiran | 5 | Done
Sprint Outcome: All preprocessing complete; 67 train/17 val split confirmed; U-Net built and compiled. Element 1 report submitted 9 Jan 2026.
Sprint 4 — Model Training & Evaluation ¦ 10 Jan – 28 Feb 2026
Sprint Goal: Train the U-Net model, evaluate performance on unseen test data, and implement improved bacteria counting.
Backlog ID | Task | Owner | Points | Status | Sprint Total Story Points
PB-15 | Train U-Net: 150 epochs, EarlyStopping, ModelCheckpoint, ReduceLROnPlateau | Kiran | 21 | Done | 81
PB-16 | Configure training callbacks (early stop at epoch 110, best at epoch 90) | Kiran | 8 | Done
PB-17 | Compute Dice, IoU, Precision, Recall on 5 test images | Jenish | 13 | Done
PB-18 | Plot training/validation Dice and Loss curves | Jenish | 5 | Done
PB-19 | Basic connected-components bacteria counting | Jenish | 8 | Done
PB-20 | Watershed algorithm counting (78% error reduction: 64 → 14) | Jenish | 13 | Done
PB-21 | End-to-end inference pipeline: upload → predict → count → display | Kiran | 13 | Done
Sprint Outcome: Best val Dice = 0.8235 (epoch 90). Test metrics: Dice 79.6%, IoU 66.2%, Precision 76.9%, Recall 83.3%. Watershed total error = 14.
Sprint 5 — Dashboard, Exhibition & Submission ¦ 1 Mar – 27 Apr 2026
Sprint Goal: Build and deploy the Streamlit dashboard, prepare and deliver the exhibition, and submit all final reports.
Backlog ID | Task | Owner | Points | Status | Sprint Total Story Points
PB-22 | Build Streamlit dashboard: upload, inference, visualisation, metrics | Kiran | 13 | Done | 34
PB-23 | Add export features: JSON, CSV, Report PNG, Mask PNG | Kiran | 5 | Done
PB-24 | Deploy dashboard via localtunnel for live exhibition URL | Kiran | 3 | Done
PB-25 | Design and print A1 exhibition poster | All Members | 5 | Done
PB-26 | Submit individual Element 2 completion reports to Canvas | All Members | 8 | In Progress
Sprint Outcome: Streamlit dashboard live at bacteriaai.loca.lt; poster presented 21 April; group demo completed. Individual reports due 27 April.

## Project Plan
PROJECT PLANNING
| Project Title: Bacterial Diagnostic and Quantification using AI |  |  |  | Company Name: |  | Smart Bio Detective
[6 empty] | Date: | 2025-11-05
[9 empty] | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May
S.N | SPRINT | TASKS | ASSIGNED TO | START DATE | DUE DATE | DURATION | DEPENDENCIES
[6 empty] | (Days) |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
| Sprint 0 | Project Initiation
|  | 1. Team Setup | All members | 2025-10-06 | 2025-10-07 | 1
1.1. Created team contract | bar: W1
|  | 2. Project Selection | All members | 2025-10-06 | 2025-10-08 | 2
2.1. Selected Project - Bacterial Diagnostics and Quantification Using AI | bar: W2
2.2. Assigned role to each members | bar: W2
|  | 3. Project Setup | All members | 2025-10-09 | 2025-10-16 | 7 | Project selection | bar: W3
3.1. Set uo Github, folders and communication tools | bar: W3
| Sprint 1 | Project Planning
|  | 1. Client Engagement | All members | 2025-10-18 | 2025-10-21 | 3 | bar: W4
1.1. Initial meeting with client | bar: W4 to W1
|  | 2. Project Requirement | All members | 2025-10-18 | 2025-10-28 | 10 | Client Engagement | bar: W1 to W2
2.1. Defined aims and objectives of project | bar: W2
2.2. Talked about scope and success criteria | bar: W3
|  | 3. Data Collection | Member 2 | 2025-10-28 | 2025-11-07 | 9 | Prj Requirement | bar: W3
3.1. Received datasets from our client | bar: W4 to W1
|  | 4. Data Understanding | Member 2 | 2025-11-05 | 2025-11-14 | 9 | Data collection | bar: W4
4.1. Explore datasets structure and labels
| Sprint 2 | Project Research
|  | 1. Literature Review | Member 3 | 2025-11-15 | 2025-11-26 | 11 | Understanding data | bar: W1
1.1. Reviewed articals and research papers on bacterial diagnostic | bar: W1
1.2. Started researching on different models and augmentation methods | bar: W2 to W3
|  | 2. Methodology Planning | All members | 2025-11-27 | 2025-12-06 | 10 | Article reviews | bar: W3
2.1. Selected appropriate metrics and tools to support the analysis | bar: W4
2.2. Designed a structured experiment to evaluate outcomes effectively | bar: W4
| Sprint 3 | Project Design
|  | 1. Data Cleaning | Member 1 | 2025-12-07 | 2025-12-14 | 7 | Method planning | bar: W1
1.1. Checked consistency between images and masks | bar: W1 to W2
1.2. Identified missing files | bar: W2
1.3. Evaluated dataset quality for reliability | bar: W3
|  | 2. Pre-processing | Member 1 | 2025-12-14 | 2025-12-21 | 7 | Clean data | bar: W3
2.2. Resized images to a standard shape and normalized pixel values | bar: W4
2.3. Prepared and formatted masks for training | bar: W4
|  | 3. Augmentation | Member 1 | 2025-12-14 | 2025-12-27 | 12 | bar: W2
3.1. Appilied flipping as a data augmentation technique | bar: W3
3.2. Increased the size of the training dataset | bar: W3
|  | 4. System Design | All members | 2025-12-21 | 2026-01-01 | 10 | Augmentation | bar: W4
4.1. Bulid a complete model processing pipeline | bar: W4
4.2. Designed a clear architecture diagram the model | bar: W3
| Sprint 4 | Project Implementation | bar: W1
|  | 1. Model Development | Member 2 | 2026-01-03 | 2026-01-12 | 9 | System Design | bar: W1 to W2
1.1. Implemented the U-Net model withih a nootbook enviroment | bar: W2 to W3
1.2. Structured the model architecture for segmentation tasks | bar: W3
|  | 2. Model Training | Member 2 | 2026-01-11 | 2026-01-17 | 6 | U-Net model | bar: W1
2.1. Trained the model using fluorescence image data | bar: W2
2.2. Evaluted performance during the training process | bar: W2 to W3
|  | 3. Hyperparameter tuning | Member 2 | 2026-01-18 | 2026-02-01 | 13 | Training model | bar: W3
3.1. Tuned key hyperparameters such as epochs and loss function | bar: W4
3.2. Adjusted learining rates and callbacks for optimization | bar: W4
|  | 4. Save Best Model | Member 1 | 2026-02-04 | 2026-02-14 | 10 | bar: W4 to W1
4.1. Exported the best-perfoming model as an .h5 file
4.2. Document model output and resu
| Sprint 5 | Project Testing
|  | 1. Segmentation evaluation | Member 3 | 2026-02-15 | 2026-02-20 | 5 | Save best model | bar: W1
1.1. Measure Dice, IoU, precision and recall | bar: W1 to W2
|  | 2. Counting evaluation | Member 1 | 2026-02-21 | 2026-02-26 | 5 | bar: W3; W1
2.1. Test watershed counting against expected counts | bar: W3 to W1
|  | 3. Error analysis | Member 3 | 2026-02-26 | 2026-03-06 | 10 | Counting evaluation | bar: W4
3.1. Review false positives, false negatives and limitations | bar: W1
|  | 4. Sprint closure | All members | 2026-03-06 | 2026-03-13 | 7 | Error analysis
4.1. Sprint review, retrospective and update Github/blog | bar: W1
| Sprint 6 | Project Deployment
|  | 1. System integration | All members | 2026-03-13 | 2026-03-19 | 6 | Sprint Closure | bar: W4; W2
1.1. Combine model, counting and outputs into one workflow | bar: W4 to W1; W3
|  | 2. Dashboard development | Member 2 | 2026-03-20 | 2026-03-28 | 8
2.1. Create Streamlit demo/ dashboard | bar: W2
|  | 3. Deployment testing | All members | 2026-03-25 | 2026-04-05 | 11 | Develop dashboard | bar: W3
3.1. Run end-to-end testing on final pipeline | bar: W2
|  | 4. Poster and demo preparation | All members | 2026-03-29 | 2026-04-14 | 15 | Deployment test | bar: W2
4.1. Prepare exhibition poster, speaking points and backup demo

## Cost Estimation
COST ESTIMATION ¦ Bacteria AI Detection & Quantification ¦ EP7 Group ¦ COS6032-E
Based on industry-standard FTE costing methodology ¦ Project Duration: 7 months (Oct 2025 – Apr 2026)
SECTION 1 — LABOUR COST CALCULATION
Parameter | Value | Notes
Number of Team Members | 3 | Kiran, Bandika, Jenish
FTE per Member | 0.6 | Each member works 60% of a full-time equivalent
Total FTE (= Members × FTE) |  | 1.8 FTE total
Annual Salary per FTE (£) | 30000 | Industry junior AI developer rate
Total Labour Yearly Cost (TLYC) (£) |  | 1.8 × £30,000 = £54,000
Project Duration (months) | 7 | October 2025 to April 2026 inclusive
Duration as Fraction of Year |  | 7/12 ≈ 0.5833
Total Labour Cost (7 months) (£) |  | £54,000 × (7/12) ≈ £31,500
SECTION 2 — ADDITIONAL PROJECT COSTS
S.N | Cost Category | Description | Amount (£) | Justification
1 | Dataset Acquisition | DeepBacs fluorescence microscopy dataset (S. aureus) | 3000 | Provided by client / licensed research dataset
2 | Cloud / GPU Computing | Google Colab Pro or equivalent cloud GPU for model training | 100 | Required for training U-Net in reasonable time
3 | Software Tools & Licenses | Python libraries, TensorFlow, OpenCV, Streamlit (all open-source) | 60 | Minimal cost — open-source stack
4 | Miscellaneous | Poster printing (A1 colour), stationery, minor equipment | 200 | Exhibition poster + admin costs
| Subtotal — Additional Costs |  | 3360
SECTION 3 — FINAL BUDGET SUMMARY
Labour Cost (7 months) |  |  | 31500
Additional Costs Subtotal |  |  | 3360
TOTAL ESTIMATED PROJECT BUDGET |  |  | 34860
Budget Statement (for PID): The total labour yearly cost (TLYC) for three team members working at 0.6 FTE each was calculated as £54,000. Considering a project duration of seven months (7/12 of a year), the labour cost was estimated at approximately £31,500. Additional costs, including dataset acquisition (£3,000), cloud computing (£100), software tools (£60), and miscellaneous expenses (£200), resulted in a total estimated project budget of £34,860. This estimation reflects a realistic industry-level costing approach.

## Sprint Retrospective
SPRINT RETROSPECTIVE ¦ EP7 Group ¦ COS6032-E
What Went Well
• Dataset was successfully cleaned and organised with zero corrupt or missing files
• Preprocessing pipeline improved image quality significantly
• U-Net architecture was successfully designed and implemented (1.94M parameters)
• Best validation Dice coefficient of 0.8235 achieved at epoch 90
• Watershed algorithm reduced counting error by 78% (from 64 to 14 total errors)
• Streamlit dashboard deployed with full export functionality
• Team communication and collaboration were effective throughout
• All sprint goals and key milestones were met on time
What Didn't Go Well
• Preprocessing took longer than expected due to varied image quality
• Some microscopy images remained noisy even after filtering
• U-Net implementation required significantly more time than initially planned
• Google Colab session timeouts disrupted training runs
• Localtunnel configuration required multiple attempts to get working
• The dataset size (28 images) was smaller than ideal for deep learning
What We Learned
• Data quality is critical — time invested in preprocessing directly improves model performance
• U-Net is powerful but requires careful architectural decisions and tuning
• Saving model checkpoints to Drive after every improvement is essential to prevent data loss
• Watershed algorithm should be planned from the start of any cell counting project
• Agile sprint planning with clear Definition of Done criteria reduces ambiguity
• Early testing of deployment tools (localtunnel/ngrok) before exhibition day is crucial
What We Will Improve (Future Work)
• Expand training dataset with images from multiple laboratories for better generalisation
• Extend model to classify multiple bacterial species (multi-class segmentation)
• Conduct prospective clinical validation in a hospital microbiology laboratory
• Optimise model for edge deployment using quantisation or knowledge distillation
• Integrate dashboard with laboratory information systems (LIS) for clinical workflow
• Implement real-time video microscopy analysis capability

## ROAM Analysis
ROAM ANALYSIS ¦ Risk, Opportunity, Actions & Mitigations ¦ EP7 Group ¦ COS6032-E
# | Issue / Risk | Actions Taken | ROAM Status | Resolution Date
R-01 | Project topic and approach were unclear at the start | Team met with the client and supervisor and finalised the project scope as 'Bacterial Diagnostics and Quantification using AI'. Objectives documented in PID. | Resolved | Nov 2025
R-02 | Team needed a clear technical direction for the AI model | Conducted background research in Sprint 2; agreed to use U-Net CNN for image segmentation. Architecture justified in literature review. | Resolved | Dec 2025
R-03 | Fluorescent images contained noise and inconsistent quality | Applied noise reduction, normalisation (min-max), and data augmentation pipeline. 5-point cleaning check confirmed zero corrupt files. | Mitigated | Jan 2026
R-04 | Dataset size too small (28 images) for high model accuracy | Accepted as a known limitation. Horizontal and vertical flip augmentation expanded dataset to 84 samples. Supervisor informed. Dropout regularisation applied. | Accepted | Jan 2026
R-05 | Training U-Net model took long due to limited computing resources | Used Google Colab T4 GPU. Reduced augmentation overhead. ModelCheckpoint saves best weights to Drive. EarlyStopping prevents wasted training. | Mitigated | Feb 2026
R-06 | Model performance might not meet the Dice ≥ 0.80 success criterion | Iteratively tuned hyperparameters; used ReduceLROnPlateau. Best val Dice achieved = 0.8235 at epoch 90, exceeding the 0.80 target. | Resolved | Feb 2026
R-07 | Basic bacteria counting inaccurate due to touching cells | Implemented Watershed algorithm with Euclidean distance transform and peak_local_max. Total counting error reduced by 78% (64 → 14). | Resolved | Mar 2026
R-09 | Tunnel URL unavailable or requires password on exhibition day | Tested localtunnel before exhibition. Password retrieval cell (Cell 20) kept ready. Backup screenshots of running dashboard prepared. | Mitigated | Apr 2026
R-10 | Individual reports may be incomplete or submitted late | Sprint 5 explicitly allocates time for report writing. Submission deadline (27 April) tracked in project plan. | Owned | 27 Apr 2026
R-11 | Any group member was absent or did not contribute during the project. | Preventive actions: • All files stored on Shared Google Drive. • Clear task allocation documented • Weekly meetings recorded When short-term absence occured: • Tasks were redistributed between the other two members • Work was tracked and documented When long-term absence occured: • Supervisor was be informed immediately • Responsibilities were formally reassigned • Project scope was adjusted when necessary | Mitigated

## Research & Design Plan
RESEARCH & DESIGN PLAN ¦ Bacteria AI Detection & Quantification ¦ EP7 Group ¦ COS6032-E
Phase | R&D Element | Description & Goal | Primary Owner
Phase 1: Foundational Research & Design
| 1. Identify the Problem | Defining the clinical gap: current methods like culture-based manual microscopy are insufficient in LMICs — slow, error-prone, and skill-dependent. | All Members
| 2. Background Research (Literature Review) | Review similar projects, read published articles on U-Net, bacterial imaging, and segmentation metrics to justify architectural choices. | All Members
| 3. Architecture Pre-Selection | Researching and proposing suitable, lightweight Deep Learning architectures (U-Net) that meet the speed and size constraints of the project. | Jenish
Phase 2: Data Engineering & Preparation
| 4. Data Collection | The physical process of obtaining raw fluorescence microscopy images of Staphylococcus aureus from the client and the DeepBacs public dataset. | Kiran
| 5. Data Cleaning & Pre-processing | Scripts and procedures to standardise, clean, normalise, and augment the raw images (e.g., resizing to 256×256, noise removal, normalisation to [0,1]) before entering the model. | Kiran
| 6. Dataset Splitting | Dividing the clean data into three distinct, non-overlapping sets: Training (67), Validation (17), and Testing (5) using 80/20 split with random_state=42. | Kiran
Phase 3: Development & Iteration (Building the Model)
| 7. Model Implementation | Writing the code for the chosen deep learning architecture (U-Net) using TensorFlow/Keras framework. Architecture: 4 encoder blocks + bottleneck + 4 decoder blocks + skip connections. | Jenish
| 8. Model Training | Feeding the training data into the implemented model and using Google Colab T4 GPU to adjust the model weights over 150 epochs with early stopping. | Bandika
| 9. Hyperparameter Optimisation | Systematically adjusting model settings — learning rate (1e-4), batch size (8), dropout rates — to improve performance on the validation set without over-training. | Bandika
| 10. Image Analysis Pipeline Integration | Writing the code that connects the pre-processing pipeline with the model prediction and converts the output into a usable quantification report (bacteria count + segmentation mask). | Jenish
Phase 4: Evaluation, Validation & Deployment
| 11. Internal Testing (Model Evaluation) | Using the previously unseen Test Set (5 images) to measure the model's final performance against success metrics: Dice=79.6%, IoU=66.2%, Precision=76.9%, Recall=83.3%. | Bandika
| 12. User Interface (UI) Design & Prototyping | Designing the Streamlit dashboard and workflow that the clinician or technician will use to interact with the final tool — upload image, view segmentation, read bacteria count. | Bandika
| 13. External/Clinical Validation | Testing the model on data collected from entirely different sources (different microscopes, different labs) to prove generalisability. Noted as future work given project scope. | Kiran
| 14. Documentation & Reporting | Documenting the code, model performance, architecture choice, and the full R&D process for the final project report, poster, and GitHub repository README. | All Members

## Communication Plan
COMMUNICATION PLAN
Type of Communication | Frequency | Sender/Owner | Priority | Key Dates/Schedule | Delivery Method | Goals | Resources Links | Notes
weekly Stand-up / Check-in | weekly (Mon) | All Members | High | 15 minutes at the start of the defined workday. | Messaging App (WhatsApp) or Group Video Call | Synchronize daily activities, quickly identify roadblocks, and adjust immediate priorities. | https://chat.whatsapp.com/EwzKgqReZXC | Keep atleast 15 minutes. Focus on: What we did on past, what we will do today/further.
Pre-Kickoff Research Synthesis | One Time | All Members | High | October | Shared Document (Google Drive) | Combined findings from background research on AI models and data requirements to prepare and lead the client discussion. | https://drive.google.com/drive/folders/1MFMr_ KlCRIhVMPP1-Z8BOFkb94DiLxGb?usp=share_link | This represents the completed work done prior to the data acquisition phase.
Project Kick-off Meeting | 1st meeting (Scheduled) | Client & All Members | High | 12 th november, 2025 | Video Call (Teams) | Detailed discussion about the dataset, website, costing, resources and goal. | https://teams.microsoft.com/l/meetup -join/19%3ameeting_ZGQ4MDk2MzYtODUzZS00OWU3L WE3OGMtM2Y2NmQ5YzNiOThl%40thread.v2/0?context =%7b%22Tid%22%3a%22245ea2d1-4365-4726-805a-63 1eb93d93aa%22%2c%22Oid%22%3a%22275ff7f8-b91d- 482a-855e-8ea98fed840c%22%7d
Weekly Deep Dive Meeting | Weekly | All Members | Medium | Every Monday (12:00-15:00) | Physical Meeting | Detailed review of technical progress, risk management plan updates, resource allocation, and next major milestones. |  | Mandatory attendance.
Progress Update | Bi-Weekly | All Members | Medium | Agreed upon day/time after Kick-off (every other monday) | Physical Meeting | Provide high-level progress on planning and resource management. Manage expectations.
Documentation & File Updates | As needed (daily/weekly) | All Members | Low | After completing a major task | Shared Cloud Folder (Google Drive) | Ensure all code, research reports, and meeting notes are current and accessible to all members. | https://drive.google.com/drive/folders/1MFMr_ KlCRIhVMPP1-Z8BOFkb94DiLxGb?usp=share_link | Naming conventions must be strictly followed.
Technical Check-in (Deep Dive) | Monthly | All Members | Low | After achieving a major milestone (e.g., initial model training complete). | Video Conferencing | Demonstrate model performance, address technical questions, and confirm requirements for Image Analysis and Quantification.
Project Kick-off Meeting | 2nd meeting (scheduled) | Client and all members | high | 12th december, 2025 | physical meeting | Detailed discussion about the client expectation in project, and datasets. |  | clients expectations must be fulfilled.
Data set review meeting | early stage | All members | high | 2nd week of december | physical meeting | Analyze dataset quality, structure, and issues. |  | Includes missing marks and format issues.
sprint meeting | weekly | All members | medium | once in a week. | physical Meeting | Review progress, assign tasks |  | covers all phases
Technical discussion (Model training) | Frequent (during training phase) | All members | High | During week 1 of January and Feburary | Online and Physial meeting | Discuss U-Net training, hyperparameters, performance. |  | Focus on dice score improvement and tuning
Meeting with Khasayer | once | All members including supervisor | Medium | 21st of January | Online meeting (via Teams) | External support for dataset understanding. | https://teams.microsoft.com/l/meetup -join/19%3ameeting_ZGQ4MDk2MzYtODUzZS00OWU3L WE3OGMtM2Y2NmQ5YzNiOThl%40thread.v2/0?context =%7b%22Tid%22%3a%22245ea2d1-4365-4726-805a-63 1eb93d93aa%22%2c%22Oid%22%3a%22275ff7f8-b91d- 482a-855e-8ea98fed840c%22%7d | Provided some research samples and other similar resources.
Debugging session | AS needed (weekly/ monthly) | All members | Medium | During Feburary and march | Physical meeting | Resolve coding errors, GPU issues, runtime problems. |  | Includes run time crashes and memory issues.
Deployment discussion | final stage | All members. | High | April | Physical meeting | Plan streamlit dashboard and deployment | https://bacteriaai.loca.lt | Includes user interfce and output display
Dashboard development updates | Final stage | Kiran Nyaupane | High | April | Streamlit code sharing | Develop and test streamlit application | https://bacteriaai.loca.lt | Includes upload prediction and result display
Report writing and updates | often | All members | High | through out the project | Google drive, github | maintain report and documentation | https://github.com/kirannyaupane11/Bacterial-Diagnostics-and-Quantification-Using-AI | Includes final report and poster.

## Risk Management
RISK MANAGEMENT REGISTER ¦ Bacteria AI Detection & Quantification ¦ EP7 Group ¦ COS6032-E
Risk Type | Scenario | Risk to Project | Mitigation Plan | Owner | Status
Schedule (Falling Behind) | Data Pre-processing Delays: The raw data (e.g., microscopy images, genomic data) is inconsistent, poorly labeled, or requires significant time to clean and format for the Deep Learning Model. | High (Operational Impact) | Control the risk by dedicating a substantial, front-loaded phase for Data Wrangling. Define and enforce clear Data Quality Standards before moving to the Optimization phase. | Data Lead (Bandika) | closed
Schedule (Falling Behind) | Model Optimization Rework: Initial performance of the Deep Learning Model is insufficient for reliable bacterial diagnostics and quantification, forcing extensive time-consuming architectural changes. | Medium (Operational Impact) | Control the risk by establishing clear, measurable success criteria (e.g., minimum accuracy/sensitivity) before model development begins. Implement a fast iteration cycle to allow quick adjustments. | Model Development Lead (kiran) | closed
Budget (Overspend) | Cloud Computing Overspend: Costs for utilizing high-performance computing (HPC) for model training (especially for Deep Learning) exceed the initial financial estimate. | Medium (Financial Impact) | Control the risk by setting up strict budget alerts on the computing platform. Optimize the model architecture for efficiency and monitor resource usage daily. | Model Development Lead (kiran) | Mitigated
Budget (Overspend) | Need for External SME: The team lacks specific expertise in microscopy-based techniques or a specialized machine learning method necessary for Image Analysis and Quantification, requiring an expensive consultant. | Medium (Financial Impact) | Avoid the risk by performing a skills gap analysis and leveraging existing university or institutional resources before considering external hires. | Technical Lead (Jenish) | Mitigated
Technical (Operational) | Model Uninterpretability: The AI model achieves high accuracy but is too complex to explain why it made a specific diagnosis or quantification. | High (Operational Impact) | Control the risk by prioritizing Interpretable AI (XAI) techniques. Build the model to generate explainable features (e.g., highlighting bacteria regions) alongside the diagnostic output. | Project Manager (Kiran) | accepted
Technical (Operational) | Incompatibility with Traditional Methods: The AI output is not easily integrated or compared with the client's existing traditional techniques (like culture-based methods). | Medium (Operational Impact) | Control the risk by interviewing the client early to understand their existing workflow. Ensure the final output format is simple and compatible with their current reporting system. | Client Liaison (Jenish) | Mitigated
Project Failure (Operational) | Client Waives Evaluation/Validation: The client states that testing in the lab is not required. This omission bypasses the crucial Evaluation aim, risking an unusable, inaccurate model. | High (Operational Impact) | Negotiate/Minimize: Control the risk by formally documenting the client's instruction but strongly advocating for a minimum, internal validation phase using a private "hold-out" dataset. This protects the project's credibility. | Project Manager (Kiran) | Accepted
Technical (Operational) | Model Training Failure (U-Net): Training does not converge or produces unstable results. | High (Operational Impact) | Tune hyperparameters, adjust learning rate, use early stopping and checkpointing. | Model Development Lead (kiran) | Mitigated
Technical (Operational) | Google Colab Runtime Crash / GPU Limit: Sessions disconnect or GPU becomes unavailable during training. | Medium (Operational Impact) | Save model checkpoints regularly and reduce batch size to prevent crashes. | Development Team | Mitigated
Data | Dataset Imbalance / Limited Samples: Small dataset reduces model generalisation. | High (Operational Impact) | Apply data augmentation (flip, rotation) and preprocessing techniques. | Data Lead (Bandika) | Accepted
Technical (Operational) | Incorrect Segmentation Output: Model fails to detect bacteria properly. | High (Operational Impact) | Improve loss function (Dice + BCE) and refine training process. | Model Development Lead (kiran) | Mitigated
Technical (Operational) | Bacterial Counting Error: Overlapping bacteria cause incorrect counting. | Medium (Operational Impact) | Use watershed algorithm to separate clustered bacteria. | Development Team (All) | Mitigated
Deployment | Streamlit Application Failure: Dashboard does not run properly during demo. | High (Operational Impact) | Test application before demo and keep backup results/screenshots. | Deployment Lead (kiran) | Mitigated
Communication | Miscommunication During Debugging: Issues not clearly explained among team members. | Medium (Operational Impact) | Use daily updates and clear documentation in shared folders. | Team | Accepted